## Phase4
Date | Employee | Task | Description | Hours
06/12/2024 | Mike Cluett | / |  | 1:00
06/10/2024 | Mike Cluett | / |  | 11:00
06/04/2024 | Mike Cluett | / |  | 1:00
05/31/2024 | Tim Bargen | / |  | 8:00
05/28/2024 | Mike Cluett | / |  | 12:00
05/28/2024 | Malekey Boddie | / |  | 12:00
05/23/2024 | David Aceituno | Final touch ups |  | 8:00
05/23/2024 | Tim Bargen | / |  | 14:00
05/23/2024 | Mike Cluett | / |  | 11:00
05/23/2024 | Malekey Boddie | / |  | 11:00
05/22/2024 | David Aceituno | Final touch ups |  | 8:00
05/22/2024 | Tim Bargen | / |  | 10:00
05/22/2024 | Malekey Boddie | / |  | 11:00
05/22/2024 | Mike Cluett | / |  | 11:00
05/21/2024 | David Aceituno | Final touch ups |  | 10:00
05/21/2024 | MalekeyBoddie | / |  | 5:00
05/17/2024 | TimBargen | / |  | 12:30
05/16/2024 | DavidAceituno | Final touch ups |  | 10:00
05/16/2024 | Malekey | / |  | 11:00
05/16/2024 | Mike | / |  | 11:00
05/16/2024 | Tim |  |  | 11:00
05/15/2024 | David | Final touch ups |  | 10:00
05/15/2024 | Tim | / |  | 11:00
05/15/2024 | Malekey | / |  | 11:00
05/15/2024 | Mike | / |  | 11:00
05/14/2024 | David | Final touch ups |  | 10:00
05/13/2024 | Malekey Boddie | / |  | 13:30
05/13/2024 | Mike Cluett | / |  | 11:00
05/10/2024 | Tim Bargen | / |  | 12:45
05/09/2024 | Malekey Boddie | / |  | 8:00
05/09/2024 | Tim Bargen | / |  | 12:00
05/09/2024 | Mike Cluett | / |  | 11:00
05/08/2024 | Tim Bargen | / |  | 10:30
05/08/2024 | Malekey Boddie | / |  | 22:00
05/08/2024 | Mike Cluett | / |  | 11:00
05/07/2024 | Malekey Boddie | / |  | 11:00
05/07/2024 | Mike Cluett | / |  | 11:00
05/06/2024 | Malekey Boddie | / |  | 11:00
05/06/2024 | Mike Cluett | / |  | 11:00
05/03/2024 | Tim Bargen | / |  | 13:15
05/03/2024 | Malekey Boddie | / |  | 8:00
05/03/2024 | Mike Cluett | / |  | 8:00
05/02/2024 | Tim | / |  | 11:00
05/02/2024 | Malekey | / |  | 11:00
05/02/2024 | Mike | / |  | 11:00
05/01/2024 | David | / |  | 10:00
05/01/2024 | Tim | / |  | 11:30
05/01/2024 | Malekey | / |  | 11:00
05/01/2024 | Mike | / |  | 11:00
04/30/2024 | Malekey | / |  | 11:00
04/30/2024 | Mike | / |  | 11:00
04/29/2024 | David | / |  | 10:00
04/29/2024 | Malekey | / |  | 11:00
04/29/2024 | Mike | / |  | 11:00
04/26/2024 | Janice | / |  | 11:30
04/26/2024 | Malekey | / |  | 9:00
04/25/2024 | Tim | / |  | 11:30
04/25/2024 | Janice | / |  | 11:30
04/25/2024 | Janice | / |  | 11:30
04/25/2024 | Malekey | / |  | 11:00
04/25/2024 | David | trim, caulk, prime, |  | 10:00
04/24/2024 | Tim | / |  | 11:30
04/24/2024 | Janice | / |  | 11:30
04/24/2024 | Janice | / |  | 11:30
04/24/2024 | David | Trim, caulk, touch ups, |  | 10:00
04/24/2024 | Malekey | / |  | 11:00
05/27/2024 | David | Drywall | Fix a leak and path holes in kitchen and Bathroom | 8:00
04/10/2024 | David | Drywall | Paint and Door installation | 10:00
04/09/2024 | David | Drywall | Paint | 10:00
04/04/2024 | David | Drywall | Tape and Sand | 11:00
04/03/2024 | David | Drywall | Tape and Sand | 10:00
04/02/2024 | David | Drywall | Tape and Sand | 11:00
04/01/2024 | David | Drywall | Tape and Sand | 10:00
03/14/2024 | David | Drywall | boarding and taping | 10:00
03/13/2024 | David | Drywall | taping | 10:00
03/12/2024 | David | Drywall | taping | 10:00
03/07/2024 | David Aceituno | Drywall | taping | 10:00
03/06/2024 | David Aceituno | Drywall | taping | 10:00
03/05/2024 | David Aceituno | Drywall | taping | 10:00
03/04/2024 | David Aceituno | Drywall | taping | 10:00
03/01/2024 | David Aceituno | Drywall | taping | 5:00
02/29/2024 | David Aceituno | Drywall | Taping | 9:00
02/27/2024 | David Aceituno | Drywall | taping | 10:00
02/26/2024 | David Aceituno | Drywall | taping | 10:00
02/22/2024 | David Aceituno | Drywall | taping | 10:00
02/21/2024 | David Aceituno | Drywall | taping | 10:00
02/21/2024 | Tim Bargen | Drywall | / | 11:15
02/20/2024 | David Aceituno | Drywall | taping | 6:00
02/20/2024 | David Aceituno | Drywall | taping | 10:00
02/16/2024 | David Aceituno | Drywall | Prefill and taping corners | 8:00
02/15/2024 | David Aceituno | Drywall | Prefill and fixing screws | 10:00
02/14/2024 | David Aceituno | Drywall | Boarding | 10:00
02/12/2024 | David Aceituno | Drywall | / | 10:00
02/07/2024 | David Aceituno | Drywall | / | 10:00
02/06/2024 | David Aceituno | Drywall | / | 10:00
02/02/2024 | David Aceituno | Drywall | / | 7:00
02/01/2024 | David Aceituno | Drywall | Pre fill joints , coat screws, tape inside corners | 11:00
01/31/2024 | David Aceituno | Drywall | / | 10:00
01/31/2024 | Azael Santos | Drywall | / | 9:00
01/30/2024 | Azael Santos | Drywall | / | 11:00
01/26/2024 | David Aceituno | Drywall | / | 8:00
01/25/2024 | David Aceituno | Drywall | / | 10:00
01/25/2024 | Azael Santos | Drywall | / | 11:00
01/24/2024 | David Aceituno | Drywall | / | 10:00
01/24/2024 | Azael Santos | Drywall | / | 11:00
01/23/2024 | David Aceituno | Drywall | / | 10:00
01/23/2024 | Azael Santos | Drywall | / | 11:00
01/22/2024 | David Aceituno | Drywall | / | 10:00
01/22/2024 | Azael Santos | Drywall | / | 11:00
01/19/2024 | Azael Santos | Drywall | / | 10:00
01/19/2024 | David Aceituno | Drywall | Board Ceilings And Interior Walls | 8:00
01/18/2024 | Azael Santos | Drywall | / | 11:00
01/18/2024 | David Aceituno | Drywall | Board Interior Walls | 10:00
01/17/2024 | Azael Santos | Drywall | / | 11:00
01/16/2024 | Azael Santos | Drywall | / | 11:00
01/12/2024 | Azael Santos | Drywall | / | 9:30
01/12/2024 | Neil Wolthers | Drywall | / | 6:00
01/11/2024 | Azael Santos | Drywall | / | 11:00
01/11/2024 | Neil Wolthers | Drywall | / | 6:00
01/10/2024 | Azael Santos | Drywall | / | 11:00
01/10/2024 | Neil Wolthers | Drywall | / | 7:00
01/10/2024 | David Aceituno | Drywall | Board the Ceiling | 11:00
01/05/2024 | Azael Santos | Drywall | / | 8:00
01/05/2024 | David Aceituno | Drywall | Install backing to the build bulkhead behind the big beam in the hallway, install drywall in the lower part of some interior walls | 6:00
01/03/2024 | Azael Santos | Drywall | / | 11:00
01/02/2024 | Azael Santos | Drywall | / | 11:00
07/20/2023 | Azael Santos | Concrete Floor | / | 8:00
07/20/2023 | Mike Cluett | Concrete Floor | / | 8:00
07/19/2023 | Azael Santos | Concrete Floor | / | 11:00
07/19/2023 | Mike Cluett | Concrete Floor | / | 11:00
07/18/2023 | Azael Santos | Concrete Floor | / | 11:30
07/18/2023 | Mike Cluett | Concrete Floor | / | 11:30
07/17/2023 | Azael Santos | Concrete Floor | / | 11:00
07/17/2023 | Mike Cluett | Concrete Floor | / | 11:00
07/13/2023 | Azael Santos | Concrete Floor | / | 11:00
07/12/2023 | Azael Santos | Concrete Floor | / | 11:00
07/11/2023 | Azael Santos | Concrete Floor | / | 11:00
07/07/2023 | Neil Wolthers | Concrete Floor | / | 1:00
07/06/2023 | Neil Wolthers | Concrete Floor | / | 1:00
07/05/2023 | Neil Wolthers | Concrete Floor | / | 1:00
07/04/2023 | Neil Wolthers | Concrete Floor | / | 1:00
01/17/2024 | David Aceituno | Insulation | Vapour Barrier | 10:00
01/16/2024 | David Aceituno | Insulation | Vapour Barrier | 11:00
01/15/2024 | David Aceituno | Insulation | Insulate exterior walls | 11:00
01/11/2024 | David Aceituno | Insulation | Insulate exterior walls and Board interior walls | 11:00
01/04/2024 | David Aceituno | Insulation | Acoustical Sealant and tape for vapor barrier in ceiling | 10:00
01/03/2024 | David Aceituno | Insulation | Acoustical Sealant and tape for vapor barrier in ceiling | 10:00
01/02/2024 | David Aceituno | Insulation | Acoustical Sealant and tape for vapor barrier in ceiling | 11:00
12/07/2023 | David Aceituno | Insulation | Vapor Barrier | 10:00
12/06/2023 | David Aceituno | Insulation | Vapor Barrier | 10:00
12/05/2023 | David Aceituno | Insulation | Vapor Barrier | 10:00
12/04/2023 | David Aceituno | Insulation | Vapor Barrier | 10:00
04/11/2024 | David Aceituno | Interior Framing | Installing doors | 10:00
01/04/2024 | Azael Santos | Interior Framing | / | 11:00
12/15/2023 | Azael Santos | Interior Framing | / | 9:00
12/15/2023 | Mike Cluett | Interior Framing | / | 9:00
12/14/2023 | Azael Santos | Interior Framing | / | 5:00
12/14/2023 | Mike Cluett | Interior Framing | / | 5:00
12/08/2023 | Mike | Interior Framing | / | 9:30
12/07/2023 | Mike | Interior Framing | / | 10:00
12/06/2023 | Azael | Interior Framing | / | 11:00
12/06/2023 | Mike | Interior Framing | / | 10:30
12/05/2023 | Azael | Interior Framing | / | 11:00
12/05/2023 | Mike | Interior Framing | / | 11:00
12/04/2023 | Azael | Interior Framing | / | 10:00
12/04/2023 | Mike | Interior Framing | / | 11:00
11/20/2023 | David | Interior Framing | HVAC framing | 10:00
10/16/2023 | David | Interior Framing | Frame small interior walls, insulation and vapor barrier in a couple | 10:00
10/13/2023 | Azael | Interior Framing | / | 8:00
10/12/2023 | Azael | Interior Framing | / | 5:00
09/05/2023 | Azael Santos | Interior Framing | / | 11:00
08/31/2023 | Brea McLellan | Interior Framing | / | 11:30
08/30/2023 | David Aceituno | Interior Framing | Frame interior wall | 4:00
08/30/2023 | Brea McLellan | Interior Framing | / | 11:30
08/29/2023 | Azael Santos | Interior Framing | / | 11:00
08/29/2023 | Brea McLellan | Interior Framing | / | 11:30
08/28/2023 | Azael Santos | Interior Framing | / | 9:00
08/28/2023 | David Aceituno | Interior Framing | Back Framing For Drywall | 5:00
08/24/2023 | David Aceituno | Interior Framing | Finish sheething Mezzanine Floors Back Framing for Drywall | 10:30
08/24/2023 | Neil Wolthers | Interior Framing | / | 3:00
08/24/2023 | Brea McLellan | Interior Framing | / | 11:00
08/23/2023 | Azael Santos | Interior Framing | / | 11:00
08/23/2023 | David Aceituno | Interior Framing | Frame new mezzanine floor and install T&G plywood Framing for the HVAC duct | 10:00
08/23/2023 | Neil | Interior Framing | / | 3:00
08/23/2023 | Brea | Interior Framing | / | 11:30
08/22/2023 | Azael | Interior Framing | / | 11:00
08/22/2023 | David | Interior Framing | Install T&G plywood on the mezzanine floors | 10:30
08/22/2023 | Neil | Interior Framing | / | 3:00
08/21/2023 | Azael | Interior Framing | / | 11:00
08/21/2023 | Neil | Interior Framing | / | 3:00
08/18/2023 | Azael | Interior Framing | / | 9:00
08/17/2023 | Neil | Interior Framing | / | 3:00
08/17/2023 | Azael | Interior Framing | / | 11:00
08/16/2023 | Chas | Interior Framing | / | 3:00
08/16/2023 | Neil | Interior Framing | / | 3:00
08/15/2023 | Neil | Interior Framing | / | 3:00
08/15/2023 | Azael | Interior Framing | / | 11:00
08/14/2023 | Neil | Interior Framing | / | 3:00
08/14/2023 | Azael | Interior Framing | / | 11:00
08/11/2023 | AzaelSantos | Interior Framing | / | 10:00
08/10/2023 | Neil | Interior Framing | / | 3:00
08/10/2023 | AzaelSantos | Interior Framing | / | 11:00
08/09/2023 | Neil | Interior Framing | / | 3:00
08/09/2023 | AzaelSantos | Interior Framing | / | 11:00
08/08/2023 | Neil | Interior Framing | / | 3:00
08/08/2023 | Azael | Interior Framing | / | 11:00
08/03/2023 | Neil | Interior Framing | / | 3:00
08/02/2023 | Neil Wolthers | Interior Framing | / | 3:00
08/02/2023 | Azael Santos | Interior Framing | / | 11:00
08/02/2023 | Mike Cluett | Interior Framing | / | 11:00
08/01/2023 | Neil Wolthers | Interior Framing | / | 3:00
08/01/2023 | Azael Santos | Interior Framing | / | 11:00
08/01/2023 | Mike Cluett | Interior Framing | / | 4:00
07/31/2023 | Azael Santos | Interior Framing | / | 11:00
08/30/2023 | David Aceituno | Electrical | Prep wiring for the electrical panels | 6:00
07/10/2023 | Azael Santos | Plumbing | / | 11:00
07/06/2023 | Mike Cluett | Plumbing | / | 6:00
07/05/2023 | Mike Cluett | Plumbing | / | 11:00
07/04/2023 | Mike Cluett | Plumbing | / | 11:00
06/29/2023 | Mike Cluett | Plumbing | / | 11:00